## Peter
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Peter | 6 | 4 | 2 | 0 - learning & Gathering ideas, learning andorid SDK 1 - Meeting with customer, analyzing and prioritizing customer requests. 5 - attend group meeting, setup PivotalTracker, configure PivotalTracker, design and setup of presentation 6 - Installing Eclipse and Android SDK, install GitHub agent | 3 | 1 |  |  |  | 1 | 1 | 1 Learn Eclipse and Java 2 Getting familiar with GUI 3 begin developing application 4 finish setting up pivotal tracker | 5
2 | Peter | 4 | 3 | 1 | 0 - Continue to learn andoid SDK, download basic application framework 1 - work with team to prioritize customer requests 2 - review GUI design and begin implementing 3 - begin writing code for account creation screen 5 - discuss and assign stories | 1 | 0.5 | 0.5 | 1.5 |  | 0.5 |  | 1 meet with team to learn android SDK 2 continue to develop account creation | 6
3 | Peter | 7.5 | 5 | 2 | 0 - Continue to learn Android SDK 3 - Implement data storage to flat file 4 - ensure that flat file storage persisted accross sessions 5 - coordinate meetings, assist with others tasks 6 - firgure out how to use physical device for testing. | 3 | 0 | 0 | 2 | 0.5 | 2 | 1 | 0 - continue to learn SDK as needed 1 - go over customer requirements 2 - begin designing database 3 - continue implementing account management framework | 6
4 | Peter | 7 | 5 | 2 | 0 - Continue to learn Android SDK 3 - Implement data retrival from flat file 4 - ensure that flat file storage persisted accross sessions 5 - coordinate meetings, assist with others tasks 6 - firgure out how to use physical device for testing. | 3 | 0 | 0 | 2 | 0.5 | 2 | 1 | 0 - continue to learn SDK as needed 1 - go over customer requirements 2 - begin designing database 3 - continue implementing account management framework | 6
5** | Peter | 3 | 3 | 0 | 0 - Continue to learn Android SDK, specifically around camera intent 3 - continue to optimize account checking in flat file | 2 | 0 | 0 | 1 | 0 | 0 | 0 | Not sure | 1*
6** | Peter | 4 | 4 | 0 | 0 - Continue to learn Android SDK 2 - design architecture for account information 3 - begin implementing camera interface | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 - learn DB layout 2 - design accessors 3 - implement getters/setters 4 - test implementation 5 - meet with group | 6
7 | Peter | 7 | 5 | 2 | 0 - Continue to learn Android SDK 3 - implement setters for output to DB of account details 4 - test storage to DB and calling from DB 5 - group meeting and code review | 2 | 0 | 0 | 2 | 0.5 | 2 | 0 | 0 - continue to learn DB 3 - implement the rest of the account management framework (sound and picture) 4 - test account management persistance 5 - group meetings on Tuesday | 6
* - was having a family emergency that continued to the next week, minimal ability to work
** - was dealing with a family emergency.

## Rakshit
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Rakshit | 5 | 4 | 1 | 0- learning, 1- installing Eclipse, 2- Making sample template for app 5-Attending Group Discussions | 1 | 1 | 1 |  |  | 1 |  | 0- usage of Eclipse, 2- Basic Design Ideas | 4
2 | Rakshit | 4 | 3 | 1 | 0 - Learning Eclipse IDE ,5 - Group meeting, 2- Design of the basic layout for the alphabet learn part and the homepage | 1.5 |  | 1.5 |  |  | 1 |  | 3-implementation 0-learning | 5
3 | Rakshit | 5 | 4 | 1 | 0- learning designig Apps on Android, 0- learning design principles of android on application, 2-Adding Design to the Prototype and Initial Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss | 1 |  | 2 |  |  | 2 |  | 0-learning 3-implementation | 6
4 | Rakshit | 4 | 3 | 1 | 0- Learning Android Design Principles, 2- Layout Discussions for 1st Set of UI Design Implementations, 3- Initial Design Implementations, 5-Group Meetings, Design Team Meetings | 1 |  | 2 | 1 |  | 1 |  | 0-making framework -3 implementation design view for home page and revise view for settings page | 8
5 | Rakshit | 4 | 3 | 1 | 3-Implementing interative deisgn patterns, 2-Adding Design to the Prototype and Initial Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles |  |  | 1 | 1 |  | 2 |  | 2-Design of Pages for SplashScreen, 2-Design of Other Game Modes, 3-Implementation of Design of Mainpage, Alphabet Game Page, 5-Group Meeting | 5
6 | Rakshit | 5 | 3 | 1 | 0-Learning Swing,OpenGL for animations inside App and Splash Screen,1-Installing Plugins necessary, 2-Design Discussions, 3-Implementation of more design work, 5-Group Meeting | 1 | 1 | 1 | 1 |  | 1 |  | 2-Designing of the new screens, 1-Discussion of new user stories, 1-Testing Techniques for GUI, 3- Adding Comments in Code 1-Database Setup | 6
7 | Rakshit | 5 | 4 | 1 | 3-Cleaning up of UI design, 2- Design Discussions for Settings Page, 5-Group Meetings |  |  | 2 | 2 |  | 1 |  | 5-group meeting 1- finish the databse implementation | 7
8 | Rakshit | 15 | 13 | 2 | 3-implementing the timer 5-group meetings |  |  |  | 13 |  | 2 |  | 4-testing the timer 3-completing timer | 10
9 | Rakshit | 26 | 10 | 16 | 3- completing and adding final touches to the timer 4- testing the timer functionality for the whole app 5-group meetings |  |  |  | 5 | 5 | 16

## Sandeep
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Sandeep | 6 | 4 | 1 | 0- learning, 1- installing Github, 5-Attending Group Discussions | 1 | 1 |  |  |  | 1 |  | 0- Learning Java and usage of Github for version control, 2- Creating the intial repository | 4
2 | Sandeep | 5 | 4 | 1 | 0 - Learning Eclipse IDE ,5 - Group meeting, 3-Adding others to Github to see there work 3-Task assigned to complete settings for a question popup only for parents | 2 |  |  | 1.5 |  | 1 |  | 0-learning -5 Commiting the intial repository and publishing it so that others can view and can start commiting there code.3 - Start working on Alphabet learning mode in the app 5 - Group meeting | 5
3 | Sandeep | 7 | 4 | 3 | 0- Learning Eclipse IDE,3- Trying to implement a dialoguebox for the settings button. 5 - 1 hour group meeting and 2 hour overview of Java to work on coding and have a better understanding of how Android works and how our simple existing app runs. | 2 |  |  | 3 |  | 3 |  | 3- more java work and commiting code to the repository, 5-group meeting | 8
4 | Sandeep | 9 | 5 | 2 | 0- Learning Android development, 3- Implemented the Alert dialog for the settings button, 5-Group Meetings, Developer Meetings | 2 |  |  | 3 |  | 2.5 |  | 3-Implementing more on the alert, 5-group meeting | 7.5
5 | Sandeep | 7 | 4 | 2 | 3- implemented a math problem and editable text to the alert,2-Committed code to github,4-Tested if the code was running or not and then committed in github, 5-Group meetings with Co-developers |  |  | 0.5 | 3 | 1 | 2.5 |  | 3- Trying to add more stuff to the alert,5- group meeting | 6
6 | Sandeep | 6 | 4 | 2 | 0-Learning Swing, 2- Committing more code to github,3-Implementing a problem generator to generate its own math problem,4-Testing the code before committing in github, 5-Group meetings | 1 |  | 1 | 3 | 1 | 3 |  | 3- Trying to implement another alert for the wrong answer,5-group meeting | 9
7 | Sandeep | 8 | 4 | 1 | 4-Implemented Junit Testing for Settings button, 3- Trying to implement a game timer for the game mode, 5- Group Meetings |  |  |  |  | 3 | 1 |  | 3- Implementing schedule as a game timer for the game mode | 8

## Sweekriti
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Sweekriti | 4 | 3 | 1 | 0- learning, 1- installing Eclipse, 5-Attending Group Discussions | 1 | 1 |  |  |  | 1 |  | 0- Learning Java and usage of Eclipse, 2- Basic Design Ideas | 4
2 | Sweekriti | 4 | 3 | 1 | 1 - SPMP,0 - Learning Eclipse IDE ,5 - Group meeting, 2- Design of the basic layout and rough prototype layout for the application | 2.5 | 0.5 |  |  |  | 1 |  | 2- Learn implementing GUI effects in Eclipse for App 5 - Group meeting | 5
3 | Sweekriti | 5 | 4 | 1 | 0- Learning GUI and Designig Apps on Android, 0- Learning how to implement various Design Principles of Android on Application, 2-Adding Design to the Prototype and Initial Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles | 1.5 |  | 1 |  |  | 1.5 |  | 3-implementation of Design for Prototype, 2- Design for the various other pages, 0- learning more about Android App GUI principles | 5
4 | Sweekriti | 4 | 3 | 1 | 0- Learning Android Design Principles, 2- Layout Discussions for 1st Set of UI Design Implementations, 3- Initial Design Implementations, 5-Group Meetings, Design Team Meetings | 1 |  | 1 | 1 |  | 1 |  | 2-More Discussions of Layour, 3-Implementation of more designs in the application, 5 - Group meeting | 4
5 | Sweekriti | 5 | 4 | 1 | 3-Implementing interative deisgn patterns, 2-Adding Design to the Prototype and Initial Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles |  |  | 1.5 | 1.5 |  | 2 |  | 2-Design of Pages for SplashScreen, 2-Design of Other Game Modes, 3-Implementation of Design of Mainpage, Alphabet Game Page, 5-Group Meeting | 4
6 | Sweekriti | 4 | 3 | 1 | 0-Learning Swing,OpenGL for animations inside App and Splash Screen,1-Installing Plugins necessary, 2-Design Discussions, 3-Implementation of more design work, 5-Group Meeting | 1 | 0.5 | 0.5 | 1 |  | 1 |  | 2-Designing of the new screens, 1-Discussion of new user stories, 1-Testing Techniques for GUI, 3- Adding Comments in Code 1-Database Setup | 5
7 | Sweekriti | 4 | 3 | 1 | 3-Cleaning up of UI design, 2- Design Discussions for Settings Page, 5-Group Meetings |  |  | 1.5 | 1.5 |  | 1 |  | Cleaning up of Accounts and Settings Page, Interactive Buttons and Grid Background Changes | 4
8 | Sweekriti | 5 | 4 | 1 | 3-Implementing interative deisgn patterns, 2-Adding Design to the Prototype and Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles |  |  | 2 | 1 |  | 2 |  | Editing Images for Default App Use, Adding the Button Push Animation, Adding Default Data to Database | 7
9 | Sweekriti | 7 | 4 | 3 | 3-Implementing Game Mode for App, 2-Adding Design to the App and Commit to GitHub with Designs, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles | 0 |  | 2 | 2 |  | 3 |  | Creating Consistent UI, Implementing Game mode, Adding Click Effect for Buttons | 8

## Chitra
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Chitra | 5 | 4 | 1 | 0 - learning & Gathering ideas 1 - Installing Eclipse 5 - attend group meeting, discuss. ... | 2 | 1 |  |  |  | 1 |  | 1. Learn Eclipse and Java. 2 Getting familiar with GUI | 8
2 | Chitra | 6 | 5 | 1 | 0- learning Eclipse,coding stuff and playing around GUI 1 - Sellected Images for the app 3 - Creating database for the app images 5 - Group meetings | 3 |  | 2 |  |  |  |  | Design page, learning android app | 6
3 | Chitra | 5 | 3 | 2 | 0 - learning Eclipse and Java 1 - Writing SPMP 2 - Looking some design aspects 5 - Group Meeting | 2 | 1 | [5 empty] | SPMP, Continue Designing | 6
4 | chitra | 4 | 3 | 1 | 0- learning design principles of android on application,SQLiteconcepts 2-Making database for the image created 5- meeting with group and co-worker | 1 | 2 | [5 empty] | learn SQLite for storing images, Commit to github with design
5 | chitra | 3 | 2 | 1 | 2- Updated SPMP 5- group meetings |  | 1 | [5 empty] | spend time for splash screen creation
6 | chitra | 4 | 3 | 1 | 0- learning swing for developing splash screen 2-comited to gitgub with design 3- UI design work 5- group meeting,co-worker meeting | 2 |  | 0.5 | 0.5 |  |  |  | Need to collect some game mode ideas, commit more to git hub
7 | chitra | 5 | 5 |  | 0- learning Junit testing 3 - Changes in the appareance of the app |  |  |  | 5 |  |  |  | tesing, presentaion slide, document update,
8 | chitra | 8 | 3 | 5 | 1- Learning database implementation 3- Making changes in the UI and cleanup and finally commit the work to github 5- group meeting 6- documentation |  |  |  | 3 |  | 5 |  | Final presentation work, documentation, Gaining knowledge of setting voice, final UI clean up and testing
9 | Chitra | 11 | 1 | 10 | 3- Final editing work in SPMP and presentation slide. Updates in UI, Group meeting. | [5 empty] | 10

## Jasjot
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Jasjot Singh | 3 | 2 | 1 | 0-learning eclips and git hub 1-installing eclips 5- team meeting | 1 | 1 |  |  |  | 1 |  | 0-learning Eclips,lerning github 1-write user story | 3
2 | Jasjot Singh | 4 | 3 | 1 | 0-learning eclips 1-user story 5-meeting | 1 | 1 |  |  |  | 1 |  | 0-learning 3-implementation | 4
3 | jasjot Singh | 5 | 4 | 1 | 0-eclips git hub 3-trying to implement list in app | 3 | 1 |  |  |  | 1 |  | 0-learning 3-implementation | 5
4 | jasjot Singh | 5 | 4 | 1 | 1-learning the relation of code with in the project, 3-implementing number story,4- testing number story, 5-team meating | 1 |  |  | 1.5 | 1.5 | 1 |  | 3-implementation, 4-testing | 5
5 | jasjot Singh | 4 | 3 | 1 | 3-trying to implement the colour game ,4-testing |  |  |  | 2 | 1 | 1 |  | 3-implementation, 4-testing | 5
6 | jasjot Singh | 5 | 4 | 1 | 3-implemeting the colour and sounds, 4-testing |  |  |  | 3 | 1 | 1 |  | 3-implementation, 4-testing
7 | jasjot Singh | 7 | 6 | 1 | 2- Design the data base model 3-implemeting the databse for the various classess, 4-testing the implementation and designe |  |  | 3 | 2 | 1 |  |  | 2-design database,3-implement the designe,4-test
8 | jasjot Singh | 8 | 7 | 1 | 2- design the databse for the alphabetss, 3-implement the database and misllenious functions,4-test implementation |  |  | 2 | 4 | 1 |  |  | 2-design,3-implementation,4-test
9 | jasjot Singh | 13 | 11 | 1 | 2- design the databse for the alphabetss, 3-implement the misllenious functions,4-database test implementation,5-group meeting |  |  | 3 | 5 | 5

## isha
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Isha | 11 | 7 | 1 | 0-learning android programming,1-requirement analysis, installing eclipse 5-group discussions | 4 | 5 |  |  |  | 2 |  | 0-making framework -3 implementation design view for home page and revise view for settings page | 5
2 | Isha | 10 | 8 | 1 | 0 - Learning Eclipse IDE ,4-Deciding what test cases to be used in first and second iteration,writing meeting minutes, 5 - Group meeting, | 4 |  |  |  | 4 | 2 |  | 0-Learning Eclipse IDE,2-making a database of the images used of the alphabet, 5-group meeting | 5
3 | Isha | 11 | 4 | 1 | 0-Learning Eclipse IDE,2-making a database of the images used of the alphabet, 5-group meeting | 5 |  | 5 |  |  | 1 |  | 0-Learning Eclipse IDE,5-Group Meeting | 5
4 | Isha | 10 | 4 | 1 | 0- Learning Android development, 2-dico-scussion on what all to be included in the Iteration 1 presentation, 5-Group Meetings, Co-Developer Meetings | 5 |  | 4 |  |  | 1 |  | 1-Completing SPMP ,0-Learning Eclipse IDE,5-Group Meeting | 6
5 | Isha | 10 | 9 | 1 | 1-completing SPMP document,2-learning android programming ,4-Tested if the code was running or not , 5-Group meetings |  | 3 | 3 |  | 2 | 2 |  | 0-Learning Eclipse IDE2-completing Iteration 1 presentation,5-Group meeting | 5
6 | Isha | 10 | 8 | 1 | 0-Learning Swing,OpenGL for animations inside App and Splash Screen,1-Installing Plugins , 2-Preparing presentations for iteration 1, 3-Implementation of more design work, 5-Group Meeting | 4 |  | 3 | 1 |  | 2 |  | 0-Learning GUI ,5-group meeting | 6
7 | Isha | 10 | 7 | 1 | 0-Learning Junit Testing,android programming,2-Deciding presentaion details,writing meeting minutes5-Group meeting | 4 |  | 4 |  |  | 2 |  | 0-Learning DB implementation,Testing,2-making presentation,5 Groupmeeting | 7
8 | Isha | 14 | 8 | 1.5 | 0-learning database implementation 2-making table timer,3-making changes to the default individual images of the numbers,sounds ,colours 5- group meeting | 4 |  | 4 | 5 |  | 1 |  | 2-making font type permanent instead of changing everytime,changing position of buttons for settings page,5-group meeting | 7
9 | Isha | 15 | 8 | 2 | 1-completing spmp and SDD, 2-Preparing presentation, 5-Group Meeting, 5- Co-Designer Meeting to discuss design styles |  | 4 | 5 |  |  | 2

## Kevin
week # | Name | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
1 | Kevin | 3 | 1.5 | 1.5 | 0 - Installing Android SDK, getting up to speed with SDK, etc 5 - Group meeting | 1.5 |  |  |  |  | 1.5 |  | 1 - Complete section 4 of SPMP 1 - Create stories and associated tasks in Pivotal Tracker for initial commit of skeleton app with hooks in place 3 - Create initial app skeleton and commit to GitHub (implementation only because we need the skeleton, no functionality yet aside from very basic inner workings of the app) 5 - Group meeting | 6
2 | Kevin | 5 | 4 | 1 | 1 - SPMP 3 - App skeleton 5 - Group meeting |  | 2 |  | 2 |  | 1 |  | 3 - Start working on Alphabet learning mode in the app 5 - Group meeting | 7
3 | Kevin | 7 | 4 | 3 | 3 - Alphabet story (created swipe view to display letter/word/image on each page, and created grid view to display all letters) 5 - 1 hour group meeting and 2 hour overview of Java to give people coding right now a better understand of how Android words and how our simple existing app functionality works |  |  |  | 4 |  | 3 |  | 3 - More Java tasks (not sure which ones yet, depend on remaining functionality discussed in meeting) 5 - Group meeting | 5
4 | Kevin | 5.5 | 4 | 1.5 | 3 - more work on the alphabet learn mode 5 - 1 hour group meeting and 30 minutes after class |  |  |  | 4 |  | 1.5 |  | 3 - More java tasks (plan to setup the database) 5 - Group meeting
5 | Kevin | 6.5 | 5 | 1.5 | 3 - setup database (initial commit) 5 - 1 hour group meeting and 30 minutes after class |  |  |  | 5 |  | 1.5 |  | 5 - Group meeting
6 | Kevin | 8.5 | 7 | 1.5 | 3 - continued refining database and learn mode 5 - 1 hour group meeting and 30 minutes after class |  |  |  | 7 |  | 1.5
7 | Kevin | 10 | 9 | 1 | 3 - continued refining database and learn mode 5 - 1 hour group meeting |  |  |  | 9 |  | 1
8 | Kevin | 15.5 | 14 | 1.5 | 3 - continued refining database and learn mode 5 - 1 hour group meeting and 30 minutes after class |  |  |  | 14 |  | 1.5
9 | Kevin | 30.5 | 14 | 16.5 | 3 - continued refining database and learn mode 5 - met 6.5 hours on Tuesday night, 7 hours on Wednesday night, and 3 hours before class on Thursday |  |  |  | 14 |  | 16.5